# Postgres to Azure SQL Conversion

BioCreative Strategies

Prepared for CARR Biosystems (Barry-Wehmiller)

July 21, 2026

Table of Contents

# 07 — Postgres → Azure SQL (T-SQL) Conversion: Difficulty + Data-Transfer Runbook

The “how hard is it / what would we do” doc. Scopes converting CARR’s Supabase Postgres code + schema to Azure SQL (T-SQL) and moving the data, now that BW IT has locked Azure SQL as the target (6/17 IT call). Grounded in a live census of the CARR DB (drzxmokguptvwptuqjcv, PG17, 2026-06-27) + official Microsoft docs + the tooling landscape. Triggers: “postgres to azure sql”, “t-sql conversion”, “how hard is the azure sql migration”, “convert plpgsql”, “azure sql rls”, “data transfer to azure sql”. Supersedes the “Azure SQL = don’t” framing in 01_data_layer.md / 05_carr_migration_map.md by client decision — see banner.

## ⚠ Client decision banner (2026-06-17 IT call)

BW IT (Venkata, BW DBA lead, via Chad; confirmed by Nancy + Heather) made Azure SQL the stake-in-the-sand database target — NOT Postgres. Rationale: BW has no other Postgres anywhere except a small DI team; align to the BW standard. Our own 6/17 deep research (01_data_layer.md) argued the opposite (PG Flexible Server = near lift-and-shift; Azure SQL = “catastrophic” rewrite). That counter-argument is preserved for the record but is no longer the working plan. This doc scopes the Azure SQL rewrite as the accepted path. Flavor (Managed Instance vs SQL Database vs SQL-on-VM) was not pinned on the call — see §6.

## ✅ Target instance provisioned (2026-07-21)

BW has since stood up the destination Azure SQL database and set up BioCreative’s access:

- Server: cbsuse-sql01.database.windows.net · Database: siplatform

- Access: SSMS + MFA + BW credentials; BioCreative login Brian.Elbert@carrbiosystems.com (provisioned by Landon, BW).

- Status: pending credentials. The BW/CARR email credentials for that login are not yet issued (Colby -> Chad Evans). The conversion + data transfer in this doc begin the moment those credentials land — this is the current gating item.

The .database.windows.net endpoint indicates an Azure SQL Database logical server (not Managed Instance / SQL-on-VM); confirm the exact tier with BW cloud ops, and note the MI-vs-SQL-Database feature differences in §6 still apply. Live status + open questions: 15_migration_status.md.

## Verdict (the answer, up front)

This is a major rewrite, not a port — and there is no first-party Microsoft tool that does it. The relational shape (86 tables, FKs, indexes) moves with modest effort, but everything that makes CARR’s app work lives in Postgres-specific code that has no automated PG→T-SQL converter from Microsoft (SSMA does not support PostgreSQL as a source). The heavy mass:

- 131 functions (103 PL/pgSQL + 28 SQL) → hand/agent-rewrite to T-SQL stored procs/functions.

- 252 RLS policies across 78 tables (120 reference auth.uid()) → re-engineer as Azure SQL SECURITY POLICY + inline predicate functions reading SESSION_CONTEXT.

- 101 views, 46 triggers, 80 JSONB columns, 105 array columns → each needs T-SQL-dialect rewrites.

- In-DB networking (pg_net, http) + supabase_vault + pg_cron (21 jobs) → have no in-database Azure SQL equivalent; they move out of the database (Azure Functions / Key Vault / SQL Agent or Elastic Jobs).

Rough order of magnitude: a multi-week to multi-month effort for the data tier alone, dominated by the 131 functions + 252 policies. This is exactly why automating the repetitive tail (LLM-assisted, with human review) is worth it — and why this isn’t a copy-clone.

## Live CARR DB census (denominator for every estimate)

Source: drzxmokguptvwptuqjcv, public schema, 2026-06-27.

| Object | Count | Conversion weight |
| --- | --- | --- |
| Tables | 86 | Low — DDL maps cleanly |
| Views | 101 | Medium — dialect rewrites (casts, ->>, ::, functions) |
| Functions (PL/pgSQL) | 103 | High — procedural rewrite to T-SQL |
| Functions (SQL) | 28 | Medium |
| SECURITY DEFINER functions | 80 | High — execution-context semantics differ |
| Triggers | 46 | Medium–High — T-SQL triggers are set-based, not FOR EACH ROW |
| RLS policies | 252 (on 78 tables) | High — full re-engineering |
| — of which reference auth.uid() | 120 | High — identity source changes |
| JSONB columns | 80 | Medium — JSONB → NVARCHAR(MAX) + JSON_VALUE/OPENJSON |
| Array columns | 105 | High — T-SQL has no array type; needs redesign (junction tables / JSON) |
| gen_random_uuid() defaults | 74 | Low — → NEWID() / NEWSEQUENTIALID() |
| Sequences | 1 | Low |
| Enum types | 0 | — (none; good) |
| pg_cron jobs | 21 | Medium — → SQL Agent (MI) or Elastic Jobs (SQL DB) |
| Extensions | http, pg_cron, pg_net, pg_stat_statements, pgcrypto, supabase_vault, uuid-ossp | see §3 |

## 1. What carries / adapts / rewrites (per object type)

| Construct | Carries? | Azure SQL target | Effort | Notes |
| --- | --- | --- | --- | --- |
| Tables, columns, PK/FK, indexes | ✅ adapts | CREATE TABLE (T-SQL types) | S | Type remap: uuid→UNIQUEIDENTIFIER, text→NVARCHAR(MAX), timestamptz→DATETIMEOFFSET, boolean→BIT, numeric→DECIMAL, bytea→VARBINARY(MAX). |
| JSONB columns (80) | ⚠ rewrite | NVARCHAR(MAX) + ISJSON check constraint; query via JSON_VALUE/JSON_QUERY/OPENJSON | M | Lose binary/GIN indexing; add computed columns + indexes for hot paths. All ->/->>/@>/jsonb_* rewritten. |
| Array columns (105) | ❌ redesign | Junction table or JSON array in NVARCHAR(MAX) | L | T-SQL has no native array. The single biggest schema-shape change. |
| PL/pgSQL functions (103) | ❌ rewrite | T-SQL stored procs / scalar/TVF functions | L | Different procedural language (RETURN QUERY, FOR..LOOP, RAISE, PERFORM, %ROWTYPE all change). |
| SQL functions (28) | ⚠ rewrite | T-SQL inline TVFs | M | Mostly dialect + set semantics. |
| Triggers (46) | ⚠ rewrite | T-SQL AFTER/INSTEAD OF triggers (set-based on inserted/deleted) | M–L | Postgres FOR EACH ROW + NEW/OLD → T-SQL operates on pseudo-tables; row-loop logic must be re-expressed set-based. |
| RLS policies (252) | ❌ re-engineer | CREATE SECURITY POLICY + inline TVF predicate | L | See §2. Postgres has per-command USING/WITH CHECK; Azure SQL uses FILTER + BLOCK predicates referencing SESSION_CONTEXT. |
| Views (101) | ⚠ rewrite | T-SQL views | M | Dialect: :: casts, coalesce/nullif ok, ->>, limit→TOP/OFFSET FETCH, boolean handling. |
| Sequences (1) + gen_random_uuid() (74) | ✅ adapts | IDENTITY/SEQUENCE; NEWID()/DEFAULT | S |  |
| now(), interval, casts | ⚠ rewrite | SYSDATETIMEOFFSET(), DATEADD, CAST/CONVERT | S | Pervasive but mechanical. |
| ON CONFLICT ... DO UPDATE | ⚠ rewrite | MERGE (or upsert pattern) | M | Appears across upsert-heavy EFs/functions. |

## 2. RLS — the hard structural change (252 policies)

Postgres couples Auth↔RLS via auth.uid(). Azure SQL has RLS too, but the model differs:

- Postgres today: CREATE POLICY ... USING (rep_id = auth.uid()) — per-table, per-command, identity read from the Supabase JWT.

- Azure SQL target: a predicate inline table-valued function + a SECURITY POLICY binding FILTER (read) and BLOCK (write) predicates to each table. Identity is read from SESSION_CONTEXT (Microsoft’s recommended pattern for SaaS/multi-tenant isolation), which the API middleware sets per connection: EXEC sp_set_session_context @key=N'user_id', @value=....

So all 252 policies become: (a) one (or a few shared) predicate function(s), (b) a SECURITY POLICY per protected table, and (c) middleware that injects identity into SESSION_CONTEXT on every request. The 120 policies that read auth.uid() all repoint to SESSION_CONTEXT('user_id'). This is the same identity-injection story as 01/05, just expressed in T-SQL instead of SET LOCAL session GUCs. This work depends on the auth swap (Supabase Auth → Entra ID) and the custom API middleware — both out of scope for this doc but prerequisites for RLS to function.

## 3. The extensions reality — these leave the database entirely

CARR’s DB uses 7 non-plpgsql extensions; several have no in-database Azure SQL equivalent:

| Extension | Use in CARR | Azure SQL story |
| --- | --- | --- |
| pg_cron (21 jobs) | scheduled jobs in-DB | No in-DB scheduler. → SQL Agent jobs (Managed Instance) or Elastic Jobs (SQL Database). 21 jobs to recreate + re-point. |
| pg_net / http | async/sync HTTP from DB (1+ function calls webhooks) | No in-DB HTTP. Logic moves to Azure Functions / Logic Apps; DB no longer calls out. |
| supabase_vault | API-key storage (HeyReach, EmailBison, Brave) | → Azure Key Vault, read by the app/Functions via Managed Identity (not from SQL). |
| pgcrypto | hashing/crypto | → T-SQL HASHBYTES/ENCRYPTBYKEY or app-layer. |
| uuid-ossp | UUID gen | → NEWID() / NEWSEQUENTIALID(). |
| pg_stat_statements | perf telemetry | → Query Store (built in). |

Implication: the “database does work on its own” model (cron + HTTP + vault inside Postgres) does not survive. Those behaviors get re-homed in Azure Functions + SQL Agent/Elastic Jobs + Key Vault. That’s an architecture change, not a translation — and it’s why the EFs (next) and scheduling are a parallel workstream, not part of the SQL conversion.

## 4. Edge Functions are not in SQL-conversion scope

The 21 Deno/TS edge functions are application code, not database code. They port to Azure Functions (which also runs the TypeScript) — a separate workstream, not part of the SQL conversion. The SQL conversion only touches SQL embedded inside the DB objects (functions, views, policies, triggers), plus any inline SQL strings the EFs send.

## 5. Tooling landscape (verified 2026-06-27)

| Tool | Does it convert PG → Azure SQL? | Reality |
| --- | --- | --- |
| Microsoft SSMA | ❌ No | MS Learn SSMA page (updated 2026-04-24) lists sources as Access, Db2, MySQL, Oracle, SAP ASE — PostgreSQL is not a supported source. (A Feb-2026 trade-press piece claiming PG support is in error vs the official docs.) |
| Azure DMS | ❌ No | DMS does homogeneous PG→PG (and other matched pairs); it does not convert PG→Azure SQL. |
| Ispirer Toolkit | ⚠ Partial (commercial) | Markets a “PostgreSQL → Azure SQL Database” path; claims ~50% time reduction via automation — i.e., automates schema/data + a chunk of code, leaves the hard procedural/RLS tail manual. |
| DBConvert | ⚠ Partial (commercial) | PG↔SQL Server schema + data + optional two-way sync; strong on tables/data, weak on procedural logic. |
| LLM-assisted conversion | ✅ for the tail | Best fit for the 103 PL/pgSQL functions + 252 RLS policies + Supabase-isms that commercial tools leave behind, and re-runnable as migrations evolve. |

Net: no turnkey path exists. The pragmatic combo = a commercial tool (or pg_dump-driven script) for bulk DDL + data, plus LLM-assisted conversion for the procedural/RLS/Supabase-ism tail, plus manual review.

## 6. Which Azure SQL flavor? (open question for BW)

The 6/17 call said “Azure SQL Server / Azure SQL / Azure SQL Managed Instance” loosely — never pinned. It matters a lot:

|  | Azure SQL Managed Instance | Azure SQL Database | SQL Server on VM |
| --- | --- | --- | --- |
| Scheduler for our 21 cron jobs | SQL Agent (native) ✅ | Elastic Jobs (external, more setup) ⚠ | SQL Agent ✅ |
| Cross-DB queries / linked servers | ✅ | ❌ | ✅ |
| Closeness to full SQL Server | Highest (PaaS) | Single-DB PaaS | Full (IaaS, you patch it) |
| Fit for CARR | Best landing | Cheaper, more constraints | Defeats BW managed-cloud mandate |

Recommendation: Azure SQL Managed Instance — SQL Agent absorbs the 21 cron jobs with least redesign, and the cross-DB/T-SQL surface is closest to what CARR’s functions assume. Take back to Venkata/Chad: “Which Azure SQL — Managed Instance, SQL Database, or SQL-on-VM?” — resourcing depends on it.

## 7. Data-transfer runbook (schema → data → validate → cutover)

Data is tiny (~4,184 companies / ~104K contacts, <500 MB) — the data move is easy; the schema/code is the work. Because DMS/SSMA don’t do PG→Azure SQL, the path is:

- Convert schema to T-SQL (LLM-assisted conversion + tool, reviewed) → run on an empty Azure SQL target.

- Convert code objects (functions, views, triggers, RLS) → deploy to target; compile-check.

- Bulk-load data — Ispirer/DBConvert, Azure Data Factory (PG source → Azure SQL sink), or scripted COPY-to-CSV → bcp/BULK INSERT. Map types (UUID, JSONB→NVARCHAR, arrays→junction/JSON) on the way in.

- Re-home out-of-DB behaviors — recreate 21 jobs as SQL Agent/Elastic Jobs; move pg_net/http calls to Azure Functions; secrets to Key Vault.

- Validate — row counts + checksums per table; spot-check JSON/array reshaping; confirm RLS via SESSION_CONTEXT returns the right rows per rep; confirm jobs fire.

- Cutover — freeze writes (short maintenance window is fine at this size), final delta load, point the new API middleware at Azure SQL, smoke-test, open.

Downtime tolerance is high (small data) → no need for near-zero-downtime logical replication. The risk is correctness of the converted code, not data volume.

## 8. Difficulty verdict (per area + overall)

| Area | Difficulty | Why |
| --- | --- | --- |
| Schema/DDL (tables, keys, indexes) | S–M | Mechanical type remap; arrays (105 cols) are the exception. |
| Data move (<500 MB) | S | Tool or scripted; trivial volume. |
| Views (101) | M | Dialect rewrites, volume. |
| Functions (131) | L | Procedural rewrite; the bulk of the effort. |
| Triggers (46) | M–L | Row→set semantics. |
| RLS (252 policies) | L | Re-engineer + depends on Entra/middleware. |
| Out-of-DB (cron 21, pg_net/http, vault) | M (but architecture change) | Re-home, not translate. |
| Overall data tier | Multi-week → multi-month | Dominated by functions + RLS; gated by the auth/middleware prerequisite. |

This is materially harder than the original PG-Flexible-Server plan would have been — which is the cost of the BW standardization decision, and the case for automating the repetitive tail with LLM-assisted conversion.

## Open questions

- Azure SQL flavor? MI vs SQL Database vs VM (§6). Gates scheduler + cross-DB approach.

- Who owns the auth/middleware prerequisite? RLS can’t function until Entra + SESSION_CONTEXT injection exists.

- Buy vs build for the bulk? License Ispirer/DBConvert for DDL+data and reserve LLM-assisted conversion for the tail, or LLM-only?

- Array redesign policy — junction tables (relational-pure) vs JSON columns (least churn) for the 105 array columns?

## Research anchors

- SSMA supported sources (no PostgreSQL): learn.microsoft.com/en-us/sql/ssma/sql-server-migration-assistant (updated 2026-04-24).

- Azure SQL RLS + SESSION_CONTEXT: learn.microsoft.com/en-us/sql/relational-databases/security/row-level-security; MS Q&A recommends SESSION_CONTEXT() for tenant isolation.

- MI vs SQL Database feature comparison: learn.microsoft.com/en-us/azure/azure-sql/database/features-comparison.

- Ispirer PG→Azure SQL: ispirer.com/products/migrate-postgresql-to-microsoft-azure-sql (~50% automation claim).

- Live census: CARR DB drzxmokguptvwptuqjcv, 2026-06-27 (queries in this session).